**Development Plan**

**For**

**EventBrite Clone**

**1.Design Schedule**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **No.** | **Front Site** | **Time Reqd.** | **No.** | **User Panel** | **Time Reqd.** |
| 1 | Home Page | DONE | 5 | Create an Event | DONE |
| 2 | Event Details | DONE | 6 | My Events | DONE |
| 3 | Log in | DONE | 7 | Edit Profile | DONE |
| 4 | Sign Up | DONE | 8 | My Profile | DONE |
|  |  |  | 9 | My Tickets | DONE |
|  |  |  | 10 | My Tickets View | DONE |
|  |  |  | 11 | Add Contact | DONE |
|  |  |  | 12 | My Contacts | DONE |
|  |  |  | 13 | Create A Contact List | DONE |
|  |  |  | 14 | Contact List's records | DONE |
|  |  |  | 15 | Add New Organizer | DONE |
|  |  |  | 16 | Event Manage | 21-05-2014 |
|  |  |  | 17 | Customize Order Form | 22-05-2014 |
|  |  |  | 18 | Edit Order Confirmations | 22-05-2014 |
|  |  |  | 19 | Event Type & Language | 22-05-2014 |
|  |  |  | 20 | Add News and Updates | 22-05-2014 |
|  |  |  | 21 | Create Invitations | 23-05-2014 |
|  |  |  | 22 | Manage Invitations | 23-05-2014 |
|  |  |  | 23 | Google Analytics | 26-05-2014 |
|  |  |  | 24 | Orders | 26-05-2014 |
|  |  |  | 25 | Add Attendees | 27-05-2014 |
|  |  |  | 26 | All Attendees | 27-05-2014 |
|  |  |  | 27 | Waitlist Settings | 27-05-2014 |
|  |  |  | 28 | Create Promotional Codes | 28-05-2014 |
|  |  |  | 29 | Create Affiliate Programs | 29-05-2014 |
|  |  |  | 30 | Event Design | 29/5/2014 |
|  |  |  | 31 | My Account | 2/6/2014 |
|  |  |  | 32 | Change Password | 2/6/2014 |
|  |  |  | 33 | Payment Accounts | 2/6/2014 |
|  |  |  | 34 | Email Preferences | 3/6/2014 |
|  |  |  | 35 | Multi-User Access | 3/6/2014 |
|  |  |  | 36 | Event Affiliate Program | 4/6/2014 |
|  |  |  | 37 | Eventbrite Clone Referral Program | 4/6/2014 |
|  |  |  | 38 | My Earnings | 4/6/2014 |
|  |  |  | 39 | Cancel Orders | 5/6/2014 |
|  |  |  | 40 | How It Works | 5/6/2014 |
|  |  |  | 41 | Contact Us | 5/6/2014 |
|  |  |  | 42 | Find events | 5/6/2014 |
|  |  |  | 43 | Tickets Purchase | 6/6/2014 |
|  |  |  | 44 | Organizer | 6/6/2014 |
|  |  |  | 45 | Unused Organizers | 6/6/2014 |
|  |  |  | 46 | Withdraw Amount | 6/6/2014 |
|  |  |  | 47 | Close Account | 6/6/2014 |
|  |  |  | 48 | Add Question |  |
|  |  |  |  | **Deadline** | 10/6/2014 |

**2.Development Schedule**

Technology For Development: PHP Technology, MySql Database, Framework : Codeginiter

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Module** | **Description** | **Approx Time Required** |
| **1** | **User Registration** | **Login, Signup, Social Signup, Forget Password, Reset Password** | **2-3 days** |
| **2** | **Manage Account** | **Manage user address, Change password, manage user account Information, close account** | **2 days** |
| **3** | **Create/Manage Organizer Profile** | **Create/Edit organizer profile, Organizer Profile page, Page Theme Customization** | **4 days** |
| **4** | **Create Event** | **Create/Edit Event** | **20-25 days** |
| **5** | **My Events** | **Display Events** | **1 days** |
| **6** | **Event Registration(Detail)** | **Display Event Information and customization + Theme** | **2-3 days** |
| **7** | **Search** | **Search Events** | **4 days** |
| **8** | **Event Dashboard** | **Copy/Cancel/Delete and display basic Info** | **2 days** |
| **9** | **Invite** | **Create/edit and customize invitation. Send and schedule invitation** | **10-12 days** |
| **10** | **Customize Order Form** | **3 options** | **15 days** |
| **11** | **Attendee+ Orders** | **Add/edit Attendee, display on dashboard** | **5 days** |
| **12** | **Promotional and access Code** | **Add/update, import,** | **5-6 days** |
| **13** | **Purchase** | **Event Ticket Purchase and payment** | **10 days** |
| **14** | **My Tickets** | **Create Tickets/download/ Cancel Orders** | **4-5 days** |
| **15** | **My Contacts** | **Contact List, Add/Edit Contacts, send invite and Import/Export** | **5 days** |
| **16** | **Manage Account after event** | **Unused Orgs, Referrals, Affiliate** | **10 days** |
| **17** | **Email Prefrence** | **Newsletters and updates** | **2 days** |
| **18** | **Multi User** | **Multi user access and permission** | **6 days** |
| **19** | **Content Pages** | **Static pages and Tips** | **2 days** |
| **20** | **SSO Integration/Payment gateway** | **SSO Integration/Payment gateway** | **4-5 days** |
| **21** | **Admin** | **Admin side options** | **25+ days** |
|  | **Total** |  | **~150 days** |

**3.Testing**

**12-14 days for testing**